## Sheet1
Main Module | Work Desciption | Finish Date | Comment
face detection | testing all the 5 models (HAAR,HoG,CNN,MTCNN,Mobilemet-SSD,Yolo-V3) | 21-03-22 | DONE
| customised superset of WIDER-Face dataset for benchmarking persormance (180 images) | 21-03-28 | DONE
face recognition | testing of DeepID and openface model for feature extraction | 21-04-07 | DONE
| Customized embedding vector generation and distance maching. | 21-04-08 | DONE
| Approximiate linear searching algorithm for face feature matching | 21-04-09 | DONE
| all modules intigration | 21-04-11 | DONE
| making 30 people custom dataset for performance analysis | 21-04-11 | DONE
| each module docmumentations | 21-04-15 | WORKING
webcam integration | Opencv Modules for Webcam frame processing | 21-04-13 | DONE
| Opencv Windows application for face recognition | 21-04-15 | DONE,Delivered
GUI Program and Big Watcher | Learning C# for porting python model to Quan's library | 21-04-23 | EXPECTED
| windows excutable package testing for vison application | 21-04-30 | EXPECTED